## Sprint & Backlog
PRODUCT SPRINT PLAN
| PROJECT NAME | START DATE | END DATE
Mobil Applikation für Parkleitinformationsystem
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | SPRINT BACKLOG
| Sprint 1 |  |  |  | 2021-10-13 | 2021-11-16 | 34 | Completed | ---
| Recherche Arbeit | Ähnliche Apps Forschung | Yağmur Özel |  | 2021-10-13 | 2021-10-20 | 7 | Completed
| Recherche Arbeit | Bibliothek Erforschung für Front-End Design (FlatIcon) | Yağmur Özel |  | 2021-10-13 | 2021-10-15 | 2 | Completed
| Recherche Arbeit | Passende Architektur Erforschung(MVC) | Onur Rohat Oktay |  | 2021-10-27 | 2021-11-03 | 7 | Completed
| Dokumantation | Vorbereitung der Dokumentation | Meryem Karadaş |  | 2021-10-30 | 2021-11-16 | 17 | Completed
| Dokumantation | UML Diagramm Erstellung | Mert Bayram |  | 2021-11-03 | 2021-11-10 | 7 | Completed
| Dokumantation | Use-Case Diagramm Erstellung | Ayçanur Bayındır |  | 2021-11-10 | 2021-11-16 | 6 | Completed
| Sprint 2 |  |  |  | 2021-11-27 | 2021-12-09 | 12 | Completed
| Back-End Development | Android Studio | Meryem Karadaş |  | 2021-11-27 | 2021-12-05 | 8 | Completed
| Back-End Development | Firebase | Onur Rohat Oktay |  | 2021-11-29 | 2021-12-06 | 7 | Completed
| Back-End Development | Google Maps Android Course | Ayçanur Bayındır |  | 2021-11-29 | 2021-12-03 | 4 | Completed
| Front-End Development | Adobe XD | Yağmur Özel |  | 2021-12-01 | 2021-12-04 | 3 | Completed
| Kommunikation mit dem Kunden | Sitzung mit Kunden | Mert Bayram |  | 2021-12-06 | 2021-12-09 | 3 | Completed
| Sprint 3 |  |  |  | 2021-12-09 | 2021-12-16 | 7 | Completed
| Back-End Development | Android Studio Login- Register Seite version 1 | Yağmur Özel |  | 2021-12-09 | 2021-12-16 | 7 | Completed
| Back-End Development | Android Studio Login- Register Seite version 2 | Onur Rohat Oktay |  | 2021-12-09 | 2021-12-16 | 7 | Completed
| Back-End Development | Google Maps Service Dienste und APIs | Ayçanur Bayındır |  | 2021-12-09 | 2021-12-16 | 7 | Completed
| Back-End Development | GoogleMaps-API KEY und Karte Erstellung | Meryem Karadaş |  | 2021-12-09 | 2021-12-16 | 6 | Completed
| Sprint 4 |  |  |  | 2021-12-16 | 2021-12-23 | 7 | In Progress
| Back-End Development | Google Map in Android Studio Implementieren/Maps Activity | Meryem Karadaş |  | 2021-12-16 | 2021-12-23 | 7 | In Progress
| Back-End Development/Front-End Development | Android Studio Login und Register Seite Backend/Frontend Development/ Connection with Firebase | Onur Rohat Oktay |  | 2021-12-16 | 2021-12-23 | 7 | In Progress
| Back-End Development | Android Studio Google Maps Services Requirements Solution | Ayçanur Bayındır |  | 2021-12-16 | 2021-12-23 | 7 | In Progress
| Back-End Development/Front-End Development | Android Studio Login und Register Seite Backend/Frontend Development/ Connection with Firebase | Yağmur Özel |  | 2021-12-16 | 2021-12-23 | 7 | In Progress
| Kommunikation mit dem Kunden |  | Mert Bayram |  | 2021-12-16 | 2021-12-23 | 7 | In Progress
| Sprint 5 |  |  |  | 2021-12-23 | 2021-12-30 | 7 | Not Completed
| Back-End Development | Maps Activity Design/GPS-Koordinaten speichern mit Firebase/GPS Updates | Meryem Karadaş |  | 2021-12-23 | 2021-12-30 | 7 | Not Completed
| Back-End Development | Android Studio Login und Register Seite Backend Development/Reset Password Function/ Connection with Firebase v3 | Onur Rohat Oktay |  | 2021-12-23 | 2021-12-30 | 7 | Not Completed
| Back-End Development | GPS-Koordinaten in Benutzern abrufen,Aktualisieren von GPS-Diensten | Ayçanur Bayındır |  | 2021-12-23 | 2021-12-30 | 7 | Not Completed
| Front-End Development/Github | Adobe XD/Merge Methods On Github | Yağmur Özel |  | 2021-12-23 | 2021-12-30 | 7 | Not Completed
| Front-End Development/Github | Adobe XD/Merge Methods On Github | Mert Bayram |  | 2021-12-23 | 2021-12-30 | 7 | Not Completed

## Product Backlog
PRODUCT BACKLOG
| TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS